## Read Me
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
Adoption Workbook
Working tools for Sections II and III of Cloud Is Not the Strategy: building the Cloud Adoption Framework (CAF), planning implementation, and measuring maturity.
Shaded rows and cells are the book’s examples, mostly Northstar Manufacturing Group. Replace them with your own; white cells are for your input. Drop-down lists and formulas follow the book’s definitions.
LEGEND
Example from the book (Northstar). Replace with your own.
Your input
Tab | What it is for | Book source
Application Portfolio | Assess value and readiness, and record dispositions. | Chapter 14, Tables 14.1, 14.2, 14.4
Provider Evaluation | Weight criteria and score providers against your requirements. | Chapter 16, Tables 16.1–16.2
CAF Register | Record every CAF initiative with owner, priority, dependencies, and wave. | Chapter 23, Tables 23.1–23.2
Executive View | Summarize the CAF for executives, workstream by workstream. | Chapter 23, Table 23.3
Governance Tags | Define the foundational tags and how they are enforced. | Chapter 18, Table 18.1
Exception Register | Track exceptions to expiry, with approver and owner. | Chapter 18
Recovery Tiers | Assign recovery tiers and record recovery testing. | Chapter 20, Table 20.1
AI Readiness | Assess readiness for a specific AI use case. | Chapter 21, Table 21.2
Maturity Assessment | Profile current and desired maturity by dimension. | Chapter 26, Tables 26.1–26.3

## Application Portfolio
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
Application Portfolio and Dispositions
Source: Chapter 14, Tables 14.1, 14.2, and 14.4.
Assess business value and technical readiness separately; the quadrant follows Table 14.2. Dispositions are decisions, not maturity levels.
Application | Business Owner | Technical Owner | Business Function | Criticality | Users | Technology | Hosting | Data | Dependencies | Recovery Requirements | Regulatory Requirements | Lifecycle | Current Cost | Strategic Relevance | Business value | Technical readiness | Assessment quadrant | Disposition | Primary reason
Connected Product Platform | [17 empty] | Rearchitect | Strategic digital-product growth
Legacy Expense System | [17 empty] | Replace | Mature SaaS alternatives
Manufacturing Analytics | [17 empty] | Replatform / Rearchitect | Operational analytics and AI
Legacy Plant Control System | [17 empty] | Retain | Latency, equipment, and operational dependencies
Old HR Reporting Tool | [17 empty] | Retire | Functionality duplicated elsewhere
Acquisition Integration Portal | [17 empty] | Rebuild | Standardize future acquisition onboarding
Engineering File Archive | [17 empty] | Replatform | Storage economics and global access

## Provider Evaluation
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
Provider Decision Matrix
Source: Chapter 16, Tables 16.1 and 16.2. Weights are the book’s example; adjust them to your requirements.
Score each provider from 1 (weak) to 5 (strong) against your requirements. Don’t let the spreadsheet decide: use the result to structure the decision, not to make it.
Criterion | Weight | Provider A (1–5) | Provider B (1–5) | Provider C (1–5)
Application & Platform Fit | 15%
Data & AI Capabilities | 15%
Security & Compliance | 15%
Integration With Existing Environment | 10%
Geographic & Sovereignty Requirements | 10%
Skills & Organizational Fit | 10%
Economics | 10%
Resilience | 5%
Ecosystem & Support | 5%
Exit & Portability | 5%
Weighted score (out of 5) | 100%
Weights should total 100%.
Evaluation requirements (Table 16.1)
Category | Questions
Business Alignment | Does the provider support the business capabilities identified in the strategy?
Application Fit | Does it support the architectures and applications we expect to run?
Data & AI | Does it provide the data and AI capabilities required by our roadmap?
Geographic Reach | Does it operate where our business needs to operate?
Sovereignty & Regulation | Can required workloads and data satisfy applicable requirements?
Security | Can the platform satisfy our security architecture and controls?
Resilience | Can we meet required availability and recovery objectives?
Integration | How effectively can it integrate with our existing environment?
Skills | Do we possess or can we reasonably obtain the required expertise?
Operations | Can we operate and observe the environment effectively?
Economics | What are the expected economics under realistic usage?
Commercial Relationship | What contracts, commitments, support, and licensing considerations apply?
Ecosystem | Are the required partners, software products, and integrations available?
Exit | What dependencies will we create and what would transition require?

## CAF Register
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
Cloud Adoption Framework Register
Source: Chapter 23, Tables 23.1 and 23.2; waves from Chapters 13 and 23. Example: Northstar’s completed CAF.
One row per CAF initiative. Priority is not sequence: record dependencies and waves separately. Not every CAF item needs a CIP.
Workstream | Requirement | Strategic Driver | Owner | Priority | Dependencies | Deliverable | Success Measure | Status | CIP Required? | Wave
Application Portfolio | Establish authoritative application portfolio | Acquisition integration, modernization | Enterprise Architecture | High
Application Portfolio | Classify application criticality | Resilience | Business + Technology | High
Application Portfolio | Assess application dispositions | Portfolio optimization | Architecture + App Owners | High
Skills and Organization | Establish cloud skills plan | Execution capability | Technology Leadership | High
Skills and Organization | Establish CCoE | Governance and enablement | CIO | High
Skills and Organization | Establish cloud engineering community | Continuous learning | CCoE | Medium
Provider and Platform | Select strategic cloud provider role(s) | Platform standardization | CIO + Architecture | High
Provider and Platform | Establish workload-placement policy | Cloud-smart strategy | Architecture | High
Provider and Platform | Establish enterprise landing zone | Governed cloud adoption | Platform Engineering | High
Provider and Platform | Establish self-service platform | Faster delivery | Platform Engineering | High
Security | Establish cloud IAM model | Security and scale | Security + IAM | High
Security | Establish cloud security baseline | Risk management | Security | High
Security | Integrate security into delivery pipelines | Faster secure delivery | Security + Engineering | High
Governance | Establish cloud policy framework | Controlled adoption | CCoE + Risk | High
Governance | Automate guardrails | Scalable governance | Platform + Security | High
Governance | Establish exception process | Business flexibility | CCoE | High
Financial Management | Establish cost ownership | Financial accountability | Finance + Technology | High
Financial Management | Implement showback | Cost visibility | FinOps | High
Financial Management | Establish forecasting and anomaly management | Financial control | FinOps | High
Operations and Resilience | Establish cloud operating model | Reliable services | Operations | High
Operations and Resilience | Establish observability | Service reliability | Platform + Operations | High
Operations and Resilience | Establish recovery standards | Business resilience | Operations + Architecture | High
Data, Integration, and AI | Establish data ownership | AI and analytics | Business + Data | High
Data, Integration, and AI | Establish integration and API principles | Modernization | Architecture | High
Data, Integration, and AI | Establish AI platform requirements | AI-enabled outcomes | Data/AI + Platform | High
Migration and Modernization | Establish transformation roadmap | Business outcomes | Architecture + Cloud Program | High
Migration and Modernization | Establish migration-wave methodology | Scalable execution | Cloud Program | High
Migration and Modernization | Establish decommissioning process | Cost and risk reduction | Operations + Finance | High

## Executive View
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
CAF Executive View
Source: Chapter 23, Table 23.3. Example: Northstar.
One line per workstream for executives: status as capability, the dependency that matters, the risk that could change a decision, and the next milestone.
Workstream | Overall Status | Critical Dependency | Major Risk | Next Milestone
Application Portfolio | In Progress | Business ownership | Incomplete dependency data | Wave 1 portfolio approved
Skills and Organization | In Progress | Staffing | Cloud engineering gap | CCoE launch
Provider and Platform | In Progress | IAM + network | Platform scope growth | Landing zone MVP
Security | In Progress | Platform | Policy automation gap | Baseline controls approved
Governance | In Progress | CCoE | Manual approvals | Guardrail MVP
Financial Management | Early | Metadata | Low cost ownership | Showback pilot
Operations and Resilience | Early | Observability | Recovery gaps | Tier 1 recovery standard
Data, Integration, and AI | Early | Data ownership | Poor data quality | Priority AI use cases approved
Migration and Modernization | Planned | Platform readiness | Hidden dependencies | Wave 1 applications selected

## Governance Tags
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
Foundational Governance Tags
Source: Chapter 18, Table 18.1.
Start with the few tags that answer ownership, cost, and risk questions, and enforce them through the platform.
Tag | Purpose | Required? | Allowed values / format | Enforced by
Application | Associates resource with application
Business Owner | Identifies accountable business owner
Technical Owner | Identifies responsible technology team
Cost Center | Supports financial allocation
Environment | Production, test, development, etc.
Data Classification | Drives data-related controls
Criticality | Supports operational and resilience decisions
Lifecycle | Helps identify temporary or expiring resources

## Exception Register
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
Governance Exception Register
Source: Chapter 18, “Exceptions Are Part of Governance” and “Temporary Exceptions Need Expiration Dates”.
Every exception should create a future decision: at expiry the environment becomes compliant, the exception is consciously renewed, or the resource is retired.
ID | Requested exception | Business justification | Risk | Compensating controls | Approver | Owner | Expiration or review date | Days remaining | Decision at expiry | In risk register?

## Recovery Tiers
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
Tiered Recovery Register
Source: Chapter 20, Table 20.1. RTO and RPO come from the business, through a business impact analysis (BIA).
Assign each application a tier based on business impact, then prove recovery: untested recovery is an assumption.
Tier | Business Impact | Example Recovery Approach
Tier 1 | Critical | Highly resilient architecture, aggressive RTO/RPO, frequent testing
Tier 2 | Important | Automated recovery with moderate RTO/RPO
Tier 3 | Standard | Backup and restore with longer recovery window
Tier 4 | Low | Rebuild or restore when practical
Applications
Application | Business owner | Tier | RTO | RPO | Recovery approach | Last recovery test | Met objectives in test?

## AI Readiness
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
AI Readiness Assessment
Source: Chapter 21, Table 21.2.
Assess readiness for a specific business problem, not for “AI” in general. A weakness in any one dimension can stop an experiment from becoming a production capability.
Dimension | Key question | Readiness (1–5) | Evidence | Gap / required action
Business | Do we have a meaningful problem or opportunity?
Data | Do we have usable, accessible, governed data?
Platform | Can we provide the required compute, models, storage, and services?
Integration | Can AI interact with the required enterprise systems?
Security | Can we protect data, models, identities, and tools?
Governance | What decisions and actions may the AI system make?
Skills | Can our people build, evaluate, and operate it?
Financial | Do the economics make sense at production scale?
Operations | Can we monitor quality, performance, cost, and behavior?
Legal & Regulatory | Can the use case operate within applicable obligations?
Exit | What dependencies are we creating on models, platforms, and providers?

## Maturity Assessment
CLOUD IS NOT THE STRATEGY · ADOPTION WORKBOOK
Cloud Adoption Capability Maturity
Source: Chapter 26, Tables 26.1–26.3. Example: Northstar’s maturity profile.
Maturity is a profile, not a single level. Don’t average the scores. Measure evidence, not opinion; the target is fitness for purpose, not Stage 5 everywhere.
Dimension | Current | Desired | Priority | Why | Evidence
Strategy and Business Alignment | 3 | 4 | Medium | Already the strongest dimension
Application Portfolio | 2 | 4 | Medium | Assessment can run alongside platform work
Skills and Organization | 2 | 4 | Medium | Grows with each wave rather than up front
Provider and Platform | 2 | 4 | High | Self-service and faster delivery depend on it
Security | 3 | 4 | Medium | Already relatively strong
Governance | 2 | 4 | Medium | Largely delivered through the platform
Financial Management | 2 | 4 | High | Only 45% of spend has an owner today
Operations and Resilience | 2 | 4 | High | Tier 1 recovery is at 60% against a 95% target
Data, Integration, and AI | 2 | 4 | High | The AI outcomes can’t happen without it
Migration and Modernization | 2 | 4 | Medium | Follows the platform and portfolio work
Maturity scale (Table 26.1)
Stage | Description
1 — Ad Hoc | Capability exists inconsistently or depends heavily on individuals
2 — Defined | Common expectations and approaches have been established
3 — Repeatable | The capability can be executed consistently across relevant teams
4 — Measured | Performance and outcomes are measured and actively managed
5 — Adaptive | The capability continuously improves based on evidence, automation, and changing business needs
Stage descriptions by dimension (Table 26.2)
Dimension | Ad Hoc | Defined | Repeatable
Strategy and Business Alignment | Technology-driven; outcomes unclear | Strategy, drivers, outcomes, and principles defined | Initiatives trace to strategic requirements
Application Portfolio | Incomplete inventory; opportunistic moves | Inventory, assessment, and disposition criteria defined | Consistent assessment of value, readiness, and risk
Skills and Organization | Knowledge held by a few people | Skills, roles, and decision rights documented | Training, hiring, partners, and enablement working
Provider and Platform | Teams build environments independently | Placement principles and platform standards defined | Teams consume standard environments and automation
Security | Controls vary; security arrives late | Principles, baselines, and identity standards defined | Controls built into platforms and pipelines
Governance | Depends on individual reviewers; exceptions never expire | Decision rights, policies, and exception process defined | Common controls applied across environments
Financial Management | Bills visible but not understood | Ownership, metadata, budgets, and forecasting defined | Costs attributed; owners see their consumption
Operations and Resilience | Reactive; recovery untested | Ownership, observability, SLOs, and recovery defined | Patterns applied; Tier 1 recovery tested
Data, Integration, and AI | Fragmented data; ad hoc integrations and AI | Data ownership, integration, and AI principles defined | Approved data, integration, and AI paths repeatable
Migration and Modernization | Opportunistic moves; methods vary | Disposition criteria and migration patterns defined | Waves use proven patterns; lessons reused